## Sprint1 Backlog
| Sprint1(M2-M4) |  |  | // 2 checks/week, 3 weeks to finish M2-M4
| Tasks | Responsible | Status | Initial Estimation | 1 | 2 | 3 | 4 | 5 | 6
M2: | Setup Git on everyone's machine | All | In Progress | 1
| Work with Git and get familiar with it | All | In Progress | 1
| Choose file 1, commit the changes, and push back to Git | Yuhui Zhao | Not Started | 1
| Choose file 2, commit the changes, and push back to Git | Heng Li | Not Started | 1
| Choose file 3, commit the changes, and push back to Git | Jian Shi | Not Started | 1
| Choose file 4, commit the changes, and push back to Git | Junxian Wu | Not Started | 1
| Choose file 5, commit the changes, and push back to Git | Tiancheng Gong | Not Started | 1
| Add and remove p1 in Git | Yuhui Zhao | Not Started | 0.5
| Add and remove p2 in Git | Heng Li | Not Started | 0.5
| Add and remove p3 in Git | Jian Shi | Not Started | 0.5
| Add and remove p4 in Git | Junxian Wu | Not Started | 0.5
| Add and remove p5 in Git | Tiancheng Gong | Not Started | 0.5
| Individually build his files | Yuhui Zhao | Not Started | 1
| Individually build his files | Heng Li | Not Started | 1
| Individually build his files | Jian Shi | Not Started | 1
| Individually build his files | Junxian Wu | Not Started | 1
| Individually build his files | Tiancheng Gong | Not Started | 1
| Troubleshooting | All | Not Started | 2
M3: | User Case 1 | Heng Li | Not Started | 1.5
| User Case 2 | Yuhui Zhao | Not Started | 1.5
| User Case 3 | Jian Shi | Not Started | 1.5
| User Case 4 | Junxian Wu | Not Started | 1.5
| User Case 5 | Tiancheng Gong | Not Started | 1.5
| Create Andorid project and Launches | Heng Li | Not Started | 2
| Welcome screen displays | Yuhui Zhao | Not Started | 4
| Welcome screen login | Jian Shi | Not Started | 4
| Welcome screen registration | Junxian Wu | Not Started | 5
| Selecting login brings up screen to enter information | Tiancheng Gong | Not Started | 6
| Screen displays fields for inputting user id and password | Heng Li | Not Started | 6
| Login action | Yuhui Zhao | Not Started | 4
| Cancel action | Jian Shi | Not Started | 4
| Login information database | Junxian Wu | Not Started | 3
M4: | Hold a meeting and brainstorm | Yuhui Zhao | Not Started | 1
| Design the UML Domain Model | Heng Li | Not Started | 1
| Create the UML Domain Model | Heng Li | Not Started | 3
| Add the required logout feature | Junxian Wu | Not Started | 2
| Code the "user registration screen" | Jian Shi | Not Started | 5
| Add javadoc to the code | Tiancheng Gong | Not Started | 1
| Add the registration system to the app | Yuhui Zhao | Not Started | 1
| Test the registration system and modify | Jian Shi | Not Started | 3